# 2017-2020 Projects - Condensed Plan
2018-2019
June update

The document is colour coded

Red: Not started  - 0
Orange: In progress – 4  projects
Green: Established ongoing projects – 23 projects

Purple: Completed projects – 2 projects

Blue: On hold projects - 3

Total Projects Number: 32

Dear Members, below is there yearly budget for 2018 – 19. This gets reviewed on a quarterly basis and/or when new projects arise

| Subgroup | Project No | Name of Project | Brief Description | Priority Time | Status Update | Budget |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Health and Wellbeing | 1.1a | Mental Health Peer Support (Partnerships) | Mental Health Peer Support Group | Low established | Regular Meetings: 1st and 3rd Tuesday of the Month. Coordinator: Jake Furby and Amanda Griffths Needs more volunteers in order for it to be sustainable. | Funding has come to an end. Budget: £3,000 Funding Secured: £2752 |
|  | 1.1b | York LGBT Forum App | York LGBT Forum App | Low established | App group growing steadily. | £0 – free via flic |
|  | 1.2 | Social and Friendship Groups | Facebook Groups | Low established | Katie Cole has now become our social media volunteer and has take over the online project Coordinator: Katie Cole and Jake Furby | £0 – free via facebook |
|  | 1.3 | Coffee Morning/Evening socials and York Mind Project | Morning/Evening Socials x3 | Low established | Regular Meetings 1st Saturday and 3rd Thursday of the Month Coordinator: Jake Furby | Funding has come to an end. Funding bid has been submitted. Budget: £2,000 Funding Secured £2369.00 |
|  | 1.4 | Phone Line | Change hate crime line to phone line which offers support/signposting | Low established | Phoneline set up. Coordinator: Jake Furby Phone is broke we need a new one. | Budget: £20 |
|  | 1.6 | Photography Course | Annual six-part course in basic photography leading up to York Pride | Low established | 2nd Course starts 2018 Coordinator: S’ana Yates Hospital project did not happen. We are working on a new photography project. | Budget: £100-£300 |
|  | 1.7 | Sports Social | Set up a regular Sports Social Group | High | Project needs a new lead. Funding to be obtained. Note a gay inclusive rugby team has been set up. The Forum has added this to our calendar and advertised on social media. | Budget: £100 seed fund |
|  | 1.8 | Social Hub | To establish a social hub as the Forum has grown | High | Stage 1 – consultation in progress Stage 2 – raise funds ongoing Sage 3 – implement project | Stage 2 and 3 TBC |
|  | 1.9 | Human Rights Garden | Develop a green space | Low established | Monthly sessions | Budget £300: TCV have secured funding. We got a £1,000 from Bettys for this project. |
|  | 1.10 | Community Choir | Develop a LGBT Community Choir | Low established | Project to start in July | Budget £2,000 Secured Funding £2,000 Starts in July |
|  | 1.11 | Confidence Workshops | Deliver confidence workshop | High | 1st Confidence Workshop delivered 2nd Confidence Workshop project funding bid been submitted – wont go ahead unless we have funding | 1st £14,770 (£14,770 secured) ends in Feb 2019 – completed 2nd £20,000 awaiting funding outcome |
|  | 1.12 | LGBT Terminology Booklet | A booklet describing the most common LGBT+ terms | Low established | Project completed | Budget: £500 |
|  | 1.13 | Homeless Project | A support group for LGBT+ homeless people. Training for homeless organisations | High Priority | Fundraising for the project | Budget: £1000 Secured: £450 |
|  | Total: £43,990 Funding Secured: £23, 341 |
| 2. Older People | 2.1 | Free to be Me Training | Training for care homes and in the workplace | Low established | Regular training given. Filming to commence | Budget: £500 Secured Funding: £500 |
|  | 2.2 | Ageing Without Children (AWOC)(Partnerships) | Advice/social group set up for people ageing without children | Low established | Regular meetings 2nd Wed of the month | TBC |
|  | Total: £500 Funding Secured: £500 |
| 3. Hate Crime | 3.1 | Hate Crime Support | Liaise with police, raise awareness of hate crime. | Low established | Project Completed | Budget: £1,044 Secured Funding: £1,044 £1,080.90 expenditure |
| Total: £1, 080.90 Funding Secured:£1, 044 |
| 4. Schools and Young People | 4.1 | OutWord Bound | Writing Competition in Schools/ Book Donation/School Packs | Low established | Annual Event | £2000 Breakdown £500 writing Competition £1500 – schools brochure |
|  | 4.3 | LGBT Youth Book Club | Regular Book Club | High Priority 2018 | Starting in 2019 | £2000 |
| Total:£4000 Funding Secured: £1965 |
| 5. Transgender | 5.1 | Trans Friendly York | York Third Saturday making York a Trans friendly place | Low established | Every third Saturday | TBC |
|  | 5.2 | Transgender Workshop | Provide advice for trans people | Low established | Every two months workshop takes place – is being replicated across Leeds Gender Clinic Catchment areas | £120 |
|  | 5.3 | Human Rights Walk | How safe is York for trans and LGB people | Low established | Regular walks to monitor how safe York is – to start in 2019 | £0 |
|  | Total: £120 Funding: £120 |
| 6. International | 6.1 | International Buddying System | To pair with LGBT organisations across the world | Medium Research undertaken | Project with Kenya transition housing | Fundraisers with Time Out York |
|  | 6.2 | Support For Asylum Seekers/Refugees | To work with and help TimeOut | High | Donations and promotion of group | £900 – via fundraising |
| Total: £900 |
| 7. Bisexual | 7.1 | Bisexual Social | Regular Bisexual Socials | Low established | Regular Bisexual Socials | Budget: £100 |
| Total: £100 Funding: £130 |
| 8. Funding | 8.1 | Establish Funding subgroup | To set up funding subgroup | Low -med established | Funding subgroup has been merged into committee meeting | N/A |
| 9. Events | 9.2 | Regular events | Variety of events | High | Regular events | TBC |
| Total: TBC |
| 10. Archives (joint project) | 10.1 | To set up a LGBT archive with York Explore | To set up a LGBT archive with York Explore | High | Archive subgroup has been established. Funding bid has been submitted Not successful with funding bid. | TBC |
| 11. Selby | 11.2 | Selby Mental health group | To deliver a monthly support group | Low | Closed |  |
| 12. Northallerton | 12.1 | Northallerton Socials | Regular socials in Northallerton | High | Funding bid in | £1,000 |
| Total: £1000 Funding: £0 |
| 12. No Subgroup Attached projects. Supporting LGBT Staff Networks | 12.1 | To look at ways in which we can support LGBT Staff Networks | To look at ways in which we can support LGBT Staff Networks | Med | York LGBTQIA Hospital Staff Network North Yorkshire LGBT Police Staff Network Grand Hotel LGBT Staff Network York St John University LGBT Staff Network University of York LGBT Staff Network Aviva Pride | TBC |
|  | 12.2 | LGBT Research | To look to see if we can establish the experience LGBT face when accessing healthcare services | High | Survey Completed: research to be established | £0 |
|  | 12.3 | IT infrastructure | Implement IT infrastructure project | High | Established | £2000 |
| Total: £2000 Funding: £2000 |

# Total Project Budget: £51,655.90

Funded: £29,100

Running Costs
£2090

Total Budget

£53,745.90

Note on this budget we must update our reserve policy to £500

# Finances

| 2015-2016 | 2016-2017 | 2017-2018 | 2018-2019 June update |
| --- | --- | --- | --- |
| £3861 - budget | £8802 – budget | £60,000 budget £37,000 income | £53, 745.90 budget |
| £1820 – actual spend | £5,051 – actual spend | £27,010.03 – actual spend |  |